## Intro
| Excel Multiple Project Plan Template | Get our Premium Project Management Templates
Free Excel Template by analysistabs.com
Info 4 | Excel Project Plan Template for Multiple Project Management
Usage 4 | Go to 'Projects Summary' sheet, enter the Project Details. And go to 'Data Sheet' Sheet and enter the Tasks and Timelines in the Required Columns of the Data Table. Go to 'Project Plan' sheet to visualize your project details and Gantt chart, it is updated automatically based on your data.
Share 4 | Analysistabs ™ is developing Free and Premium l Project Management Templates. Please do not share this downloaded file. Instead, you can share our free template page link with your colleagues and friends, it helps us to create better tools and more templates.
Email 4 | Please share your feedback or ask questions, Email: info@analysistabs.com
Please Visit us
Visit us for more Free Templates and Premium Templates
i Please do not delete this worksheet. Instead, you can hide the sheet.
4 Download Now
*
1

## Dashboard
Please Select a Project to View Related Tasks & Gantt. |  |  | 4 |  | All Projects | 80 Tasks Found | [6 empty] | Gantt. Scroll | [6 empty] | 0
Dashboard |  |  |  | Task ID | Top Tasks | Responsible | Start Date | End Date | Days Req. | Status | Days Comp. | Project | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07
|  |  | 0 | 0 | 0 | 1 | 2 | 4 | 3 | 4 |  | -1
|  |  |  | 1 | Project 1 - Task 1 | Person 1 | 2022-02-24 | 2022-02-28 | 5 | 100% | 5 | Project 1
| Overall Progress |  |  | 2 | Project 3 - Task 1 | Person 2 | 2022-02-25 | 2022-03-02 | 6 | 100% | 6 | Project 3
|  |  |  | 3 | Project 1 - Task 2 | Person 3 | 2022-02-26 | 2022-03-07 | 10 | 100% | 10 | Project 1
|  |  |  | 4 | Project 1 - Task 3 | Person 4 | 2022-03-01 | 2022-03-09 | 9 | 100% | 9 | Project 1
|  |  |  | 5 | Project 1 - Task 4 | Person 5 | 2022-02-25 | 2022-02-28 | 4 | 100% | 4 | Project 1
|  |  |  | 6 | Project 1 - Task 5 | Person 1 | 2022-02-28 | 2022-03-05 | 6 | 100% | 6 | Project 1
| Start Date | 2022-02-20 |  | 7 | Project 1 - Task 6 | Person 2 | 2022-02-28 | 2022-03-06 | 7 | 100% | 7 | Project 1
| End Date | 2022-03-21 |  | 8 | Project 1 - Task 7 | Person 3 | 2022-03-02 | 2022-03-06 | 5 | 100% | 5 | Project 1
| Overall Progress | 55.08% |  | 9 | Project 1 - Task 8 | Person 4 | 2022-03-02 | 2022-03-10 | 9 | 100% | 9 | Project 1
|  | 44.92% |  | 10 | Project 1 - Task 9 | Person 5 | 2022-03-03 | 2022-03-08 | 6 | 100% | 6 | Project 1
| Days Required | 29 days |  | 11 | Project 2 - Task 1 | Person 1 | 2022-02-21 | 2022-02-27 | 7 | 59% | 4.13 | Project 2
|  | 532 man-days |  | 12 | Project 2 - Task 2 | Person 2 | 2022-02-25 | 2022-03-05 | 9 | 41% | 3.69 | Project 2
|  |  |  | 13 | Project 2 - Task 3 | Person 3 | 2022-02-26 | 2022-03-05 | 8 | 0% | 0 | Project 2
|  |  |  | 14 | Project 2 - Task 4 | Person 4 | 2022-02-28 | 2022-03-06 | 7 | 49% | 3.43 | Project 2
| Total Tasks | 80 |  | 15 | Project 2 - Task 5 | Person 5 | 2022-03-01 | 2022-03-04 | 4 | 36% | 1.44 | Project 2
| Not Started(0%) | 2 |  | 16 | Project 2 - Task 6 | Person 1 | 2022-03-01 | 2022-03-06 | 6 | 54% | 3.24 | Project 2
| Inprogress(1-99%) | 58 |  | 17 | Project 2 - Task 7 | Person 2 | 2022-03-04 | 2022-03-09 | 6 | 57% | 3.42 | Project 2
| 1-25% | 11 |  | 18 | Project 2 - Task 8 | Person 3 | 2022-03-05 | 2022-03-08 | 4 | 22% | 0.88 | Project 2
| 26-50% | 30 |  | 19 | Project 2 - Task 9 | Person 4 | 2022-03-07 | 2022-03-13 | 7 | 46% | 3.22 | Project 2
| 51-75% | 15 |  | 20 | Project 2 - Task 10 | Person 5 | 2022-02-24 | 2022-02-26 | 3 | 100% | 3 | Project 2
| 76-99% | 2 |  | 21 | Project 3 - Task 2 | Person 1 | 2022-02-20 | 2022-03-01 | 10 | 100% | 10 | Project 3
| Completed(100%) | 20 |  | 22 | Project 3 - Task 3 | Person 2 | 2022-03-01 | 2022-03-05 | 5 | 100% | 5 | Project 3
|  |  |  | 23 | Project 3 - Task 4 | Person 3 | 2022-03-03 | 2022-03-09 | 7 | 100% | 7 | Project 3
|  |  |  | 24 | Project 3 - Task 5 | Person 4 | 2022-03-06 | 2022-03-12 | 7 | 100% | 7 | Project 3
Project Gantt. Template By: | https://analysistabs.com | PNRao |  | 25 | Project 3 - Task 6 | Person 5 | 2022-03-08 | 2022-03-10 | 3 | 100% | 3 | Project 3
Please let us know your feedback ¦ Email: info@analysistabs.com |  |  |  |  | i This is a free template, you can use this template to plan a small project with 25 tasks, check our premium templates for multiple projects and more features.
55%

## Projects Summary
Project Management
Projects | Tasks | Start | End | Days | %Progress | Remaining
All Projects | 80 | 2022-02-20 | 2022-03-21 | 532 | 55.08% | 44.92%
Project 1 | 9 | 2022-02-24 | 2022-03-13 | 61 | 100% | 0%
Project 2 | 10 | 2022-02-21 | 2022-03-16 | 61 | 46.4% | 53.6%
Project 3 | 6 | 2022-02-20 | 2022-03-18 | 38 | 100% | 0%
Project 4 | 7 | 2022-02-24 | 2022-03-21 | 51 | 44.43% | 55.57%
Project 5 | 8 | 2022-02-27 | 2022-03-20 | 55 | 33.88% | 66.12%
Project 6 | 8 | 2022-02-24 | 2022-03-12 | 52 | 63% | 37%
Project 7 | 9 | 2022-02-21 | 2022-03-13 | 62 | 40.56% | 59.44%
Project 8 | 11 | 2022-02-20 | 2022-03-21 | 69 | 47.91% | 52.09%
Project 9 | 4 | 2022-02-27 | 2022-03-15 | 28 | 48.25% | 51.75%
Project 10 | 8 | 2022-02-27 | 2022-03-20 | 55 | 33.88% | 66.12%
Formulas:
Start = MIN(Table1[Start Date])
Start = MIN(IF(Table1[Project]=[Projects],Table1[Start Date]))
End = MAX(Table1[Start Date])+MAX(Table1[Days Req.])
End = MAX(IF(Table1[Project]=[Projects],Table1[Start Date]))+MAX(IF(Table1[Project]=[Projects],Table1[Days Req.]))
1.
Input Your Project Title Here

## Data Sheet
Project | Task | Responsible | Start Date | Days Req. | Progress
Project 1 | Project 1 - Task 1 | Person 1 | 2022-02-24 | 5 | 100%
Project 3 | Project 3 - Task 1 | Person 2 | 2022-02-25 | 6 | 100%
Project 1 | Project 1 - Task 2 | Person 3 | 2022-02-26 | 10 | 100%
Project 1 | Project 1 - Task 3 | Person 4 | 2022-03-01 | 9 | 100%
Project 1 | Project 1 - Task 4 | Person 5 | 2022-02-25 | 4 | 100%
Project 1 | Project 1 - Task 5 | Person 1 | 2022-02-28 | 6 | 100%
Project 1 | Project 1 - Task 6 | Person 2 | 2022-02-28 | 7 | 100%
Project 1 | Project 1 - Task 7 | Person 3 | 2022-03-02 | 5 | 100%
Project 1 | Project 1 - Task 8 | Person 4 | 2022-03-02 | 9 | 100%
Project 1 | Project 1 - Task 9 | Person 5 | 2022-03-03 | 6 | 100%
Project 2 | Project 2 - Task 1 | Person 1 | 2022-02-21 | 7 | 59%
Project 2 | Project 2 - Task 2 | Person 2 | 2022-02-25 | 9 | 41%
Project 2 | Project 2 - Task 3 | Person 3 | 2022-02-26 | 8 | 0%
Project 2 | Project 2 - Task 4 | Person 4 | 2022-02-28 | 7 | 49%
Project 2 | Project 2 - Task 5 | Person 5 | 2022-03-01 | 4 | 36%
Project 2 | Project 2 - Task 6 | Person 1 | 2022-03-01 | 6 | 54%
Project 2 | Project 2 - Task 7 | Person 2 | 2022-03-04 | 6 | 57%
Project 2 | Project 2 - Task 8 | Person 3 | 2022-03-05 | 4 | 22%
Project 2 | Project 2 - Task 9 | Person 4 | 2022-03-07 | 7 | 46%
Project 2 | Project 2 - Task 10 | Person 5 | 2022-02-24 | 3 | 100%
Project 3 | Project 3 - Task 2 | Person 1 | 2022-02-20 | 10 | 100%
Project 3 | Project 3 - Task 3 | Person 2 | 2022-03-01 | 5 | 100%
Project 3 | Project 3 - Task 4 | Person 3 | 2022-03-03 | 7 | 100%
Project 3 | Project 3 - Task 5 | Person 4 | 2022-03-06 | 7 | 100%
Project 3 | Project 3 - Task 6 | Person 5 | 2022-03-08 | 3 | 100%
Project 4 | Project 4 - Task 1 | Person 1 | 2022-03-10 | 9 | 88%
Project 4 | Project 4 - Task 2 | Person 2 | 2022-03-11 | 10 | 20%
Project 4 | Project 4 - Task 3 | Person 3 | 2022-02-24 | 4 | 10%
Project 4 | Project 4 - Task 4 | Person 4 | 2022-02-27 | 8 | 60%
Project 4 | Project 4 - Task 5 | Person 5 | 2022-03-02 | 10 | 34%
Project 4 | Project 4 - Task 6 | Person 1 | 2022-03-05 | 6 | 51%
Project 4 | Project 4 - Task 7 | Person 2 | 2022-03-05 | 4 | 48%
Project 5 | Project 5 - Task 1 | Person 3 | 2022-03-08 | 8 | 32%
Project 5 | Project 5 - Task 2 | Person 4 | 2022-03-10 | 9 | 42%
Project 5 | Project 5 - Task 3 | Person 5 | 2022-02-28 | 5 | 59%
Project 5 | Project 5 - Task 4 | Person 1 | 2022-02-27 | 3 | 31%
Project 5 | Project 5 - Task 5 | Person 2 | 2022-03-01 | 7 | 49%
Project 5 | Project 5 - Task 6 | Person 3 | 2022-03-02 | 10 | 16%
Project 5 | Project 5 - Task 7 | Person 4 | 2022-03-02 | 10 | 31%
Project 5 | Project 5 - Task 8 | Person 5 | 2022-03-02 | 3 | 11%
Project 6 | Project 6 - Task 1 | Person 1 | 2022-02-24 | 5 | 47%
Project 6 | Project 6 - Task 2 | Person 2 | 2022-02-25 | 6 | 43%
Project 6 | Project 6 - Task 3 | Person 3 | 2022-02-26 | 10 | 38%
Project 6 | Project 6 - Task 4 | Person 4 | 2022-03-01 | 9 | 100%
Project 6 | Project 6 - Task 5 | Person 5 | 2022-02-25 | 4 | 100%
Project 6 | Project 6 - Task 6 | Person 1 | 2022-02-28 | 6 | 100%
Project 6 | Project 6 - Task 7 | Person 2 | 2022-02-28 | 7 | 42%
Project 6 | Project 6 - Task 8 | Person 3 | 2022-03-02 | 5 | 34%
Project 7 | Project 7 - Task 1 | Person 4 | 2022-03-02 | 9 | 14%
Project 7 | Project 7 - Task 2 | Person 5 | 2022-03-03 | 6 | 55%
Project 7 | Project 7 - Task 3 | Person 1 | 2022-02-21 | 7 | 59%
Project 7 | Project 7 - Task 4 | Person 2 | 2022-02-25 | 9 | 41%
Project 7 | Project 7 - Task 5 | Person 3 | 2022-02-26 | 8 | 0%
Project 7 | Project 7 - Task 6 | Person 4 | 2022-02-28 | 7 | 49%
Project 7 | Project 7 - Task 7 | Person 5 | 2022-03-01 | 4 | 36%
Project 7 | Project 7 - Task 8 | Person 1 | 2022-03-01 | 6 | 54%
Project 7 | Project 7 - Task 9 | Person 2 | 2022-03-04 | 6 | 57%
Project 8 | Project 8 - Task 1 | Person 3 | 2022-03-05 | 4 | 22%
Project 8 | Project 8 - Task 2 | Person 4 | 2022-03-07 | 7 | 46%
Project 8 | Project 8 - Task 3 | Person 5 | 2022-02-24 | 3 | 100%
Project 8 | Project 8 - Task 4 | Person 1 | 2022-02-20 | 10 | 47%
Project 8 | Project 8 - Task 5 | Person 2 | 2022-03-01 | 5 | 55%
Project 8 | Project 8 - Task 6 | Person 3 | 2022-03-03 | 7 | 38%
Project 8 | Project 8 - Task 7 | Person 4 | 2022-03-06 | 7 | 33%
Project 8 | Project 8 - Task 8 | Person 5 | 2022-03-08 | 3 | 68%
Project 8 | Project 8 - Task 9 | Person 1 | 2022-03-10 | 9 | 88%
Project 8 | Project 8 - Task 10 | Person 2 | 2022-03-11 | 10 | 20%
Project 8 | Project 8 - Task 11 | Person 3 | 2022-02-24 | 4 | 10%
Project 9 | Project 9 - Task 1 | Person 4 | 2022-02-27 | 8 | 60%
Project 9 | Project 9 - Task 2 | Person 5 | 2022-03-02 | 10 | 34%
Project 9 | Project 9 - Task 3 | Person 1 | 2022-03-05 | 6 | 51%
Project 9 | Project 9 - Task 4 | Person 2 | 2022-03-05 | 4 | 48%
Project 10 | Project 10 - Task 1 | Person 3 | 2022-03-08 | 8 | 32%
Project 10 | Project 10 - Task 2 | Person 4 | 2022-03-10 | 9 | 42%
Project 10 | Project 10 - Task 3 | Person 5 | 2022-02-28 | 5 | 59%
Project 10 | Project 10 - Task 4 | Person 1 | 2022-02-27 | 3 | 31%
Project 10 | Project 10 - Task 5 | Person 2 | 2022-03-01 | 7 | 49%
Project 10 | Project 10 - Task 6 | Person 3 | 2022-03-02 | 10 | 16%
Project 10 | Project 10 - Task 7 | Person 4 | 2022-03-02 | 10 | 31%
Project 10 | Project 10 - Task 8 | Person 5 | 2022-03-02 | 3 | 11%
2.
Input Your Tasks of Your Project and Respective Timelines

## Advanced Project Plan Template
Ultimate Project Plan Advanced Excel Template
The Most Powerful Project Planning Template on the Market
View Details 4
Our Most Popular Project Management Templates
Excel Templates | PowerPoint Templates | MS Word Templates
Browse All Templates4

## License
License Terms
4 | Analysistabs™ License Agreement
This Template/Excel File and sample data is created by Analysistabs™
4 | Licensed Product: Single User License to Analysistabs™ Project Plan Template
4 | Single User License: Allows 1 (Personal Use Only).
4 | You are Allowed
4 | Individual users are permitted to use this template for their personal use only
4 | You can share the template page link:(https://analysistabs.com/project/management/)
4 | You can make copies for your own use
4 | You are NOT Allowed
4 | Reproducing of this template is not permitted for reselling, rebranding, team usage, company usage, training and any other business purpose.
4 | You are not allowed to share this template, or the screenshots/ images produced using this template with sample data provided in the template.
4 | You are not allowed to share our template via Emails, Shared drives, Common Folders, Websites, and Social media
4 | You must not remove our copyright notices and Licence sheets from the template
4 | The templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others. Instead, you can share following web page link of this template.
Link: | https://analysistabs.com/project/management/