## Template Details
Project Plan Excel Template 2016
Project Planner Created using Microsoft Excel 2016
Info | Project Plan Excel Template 2016 is a free Miscrosoft Template to plan your projects. Excel Project Planner Template 2016 version helps you to plan project timelines and resource effectively. You can change the default data and formula to meet your needs. |  | Please Note: We have protected worksheets in this template to avoid the mistakes by chance. You can use the password 'PNRao' to unprotect the Worksheets
Usage | Use Excel 2016 Project Plan Template for managing your Projects with ease. You can use it for developing an IT Project or any other project which involveds tasks, resources and timelines. We have provided Gantt View of Project Plans along with overall project completion status in Excel 2016 Format.
Please Share | Project Tracking/ Project Plan / Gant. Chart Template is a Free and lite version of ANALYSISTABS' Project Management Templates. Please feel free to use, modify and share with your coleagues. | Please check our Premium Templates Bundle, all you need for effective project planning, management and presentations. Our premium templates are professional, powerfull, easy to customize and unique in style. Please visit analysistabs.com and grab our powerfull templates for nominal cost.
Please Let us know your feedback |  |  |  | info@analysistabs.com
Templates By ANALYSISTABS.For more templates and tools, please visit us: |  |  |  | htps://analysistabs.com
Premium Templates
Visit Our BLOG
ANALYSISTABS.COM
Project Gantt. 4
Data Sheet4
Advanced Templates4

## Project Plan Gantt
| Project Plan |  |  | Tasks Scrool | Task ID | Task | Rseponsible | Start Date | End Date | Days Req. | Status | Days Comp. | 2016-02-16 | 2016-02-17 | 2016-02-18 | 2016-02-19 | 2016-02-20 | 2016-02-21 | 2016-02-22 | 2016-02-23 | 2016-02-24 | 2016-02-25 | 2016-02-26 | 2016-02-27 | 2016-02-28 | 2016-02-29 | 2016-03-01 | 2016-03-02
|  |  |  | 0 |  | 0 | 1 | 2 | 4 | 3 | 4
Project Name |  |  |  |  | 1 | Task 1 | Person 1 | 2016-02-16 | 2016-02-20 | 5 | 47% | 2.35
Customer Name |  |  |  |  | 2 | Task 2 | Person 2 | 2016-02-17 | 2016-02-22 | 6 | 43% | 2.58
Project Manager |  |  |  |  | 3 | Task 3 | Person 3 | 2016-02-18 | 2016-02-27 | 10 | 38% | 3.8
[5 empty] | 4 | Task 4 | Person 4 | 2016-02-21 | 2016-02-29 | 9 | 34% | 3.06
Start Date |  | 2016-02-16 |  |  | 5 | Task 5 | Person 5 | 2016-02-17 | 2016-02-20 | 4 | 25% | 1
End Date |  | 2016-03-12 |  |  | 6 | Task 6 | Person 1 | 2016-02-20 | 2016-02-25 | 6 | 7% | 0.42
Overall Progress |  | 40.65% |  |  | 7 | Task 7 | Person 2 | 2016-02-20 | 2016-02-26 | 7 | 42% | 2.94
|  | 59.35% |  |  | 8 | Task 8 | Person 3 | 2016-02-22 | 2016-02-26 | 5 | 34% | 1.7
Days Required 6 |  |  |  |  | 9 | Task 9 | Person 4 | 2016-02-22 | 2016-03-01 | 9 | 14% | 1.26
25 days |  |  |  |  | 10 | Task 10 | Person 5 | 2016-02-23 | 2016-02-28 | 6 | 55% | 3.3
266 ManDays |  |  |  |  | 11 | Task 11 | Person 1 | 2016-02-16 | 2016-02-22 | 7 | 59% | 4.13
[5 empty] | 12 | Task 12 | Person 2 | 2016-02-17 | 2016-02-25 | 9 | 41% | 3.69
Gantt. Scroll |  |  | 0 |  | 13 | Task 13 | Person 3 | 2016-02-18 | 2016-02-25 | 8 | 0% | 0
[5 empty] | 14 | Task 14 | Person 4 | 2016-02-20 | 2016-02-26 | 7 | 49% | 3.43
Total Tasks | 40 | Remarks |  |  | 15 | Task 15 | Person 5 | 2016-02-21 | 2016-02-24 | 4 | 36% | 1.44
Not Started(0%) | 1 | Your Project Notes Here |  |  | 16 | Task 16 | Person 1 | 2016-02-21 | 2016-02-26 | 6 | 54% | 3.24
Inprogress(1-99%) | 38 | You can use this space to write |  |  | 17 | Task 17 | Person 2 | 2016-02-24 | 2016-02-29 | 6 | 57% | 3.42
1-25% | 8 | Important Business Rules |  |  | 18 | Task 18 | Person 3 | 2016-02-25 | 2016-02-28 | 4 | 22% | 0.88
26-50% | 20 | And Key Deliverables |  |  | 19 | Task 19 | Person 4 | 2016-02-27 | 2016-03-04 | 7 | 46% | 3.22
51-75% | 9 |  |  |  | 20 | Task 20 | Person 5 | 2016-02-16 | 2016-02-18 | 3 | 100% | 3
76-99% | 1 |  |  |  | 21 | Task 21 | Person 1 | 2016-02-19 | 2016-02-28 | 10 | 47% | 4.7
Completed(100%) | 1 |  |  |  | 22 | Task 22 | Person 2 | 2016-02-21 | 2016-02-25 | 5 | 55% | 2.75
[5 empty] | 23 | Task 23 | Person 3 | 2016-02-23 | 2016-02-29 | 7 | 38% | 2.66
[5 empty] | 24 | Task 24 | Person 4 | 2016-02-26 | 2016-03-03 | 7 | 33% | 2.31
Project Gantt. Template By: |  | https://analysistabs.com | PNRao |  | 25 | Task 25 | Person 5 | 2016-02-28 | 2016-03-01 | 3 | 68% | 2.04
Please let us know your feedback ¦ Email: info@analysistabs.com
Task Grid
Gantt Chart
41%

## Plans Data Sheet
Task | Responsible | Start Date | Days Req. | Progress
Task 1 | Person 1 | 2016-02-16 | 5 | 47%
Task 2 | Person 2 | 2016-02-17 | 6 | 43%
Task 3 | Person 3 | 2016-02-18 | 10 | 38%
Task 4 | Person 4 | 2016-02-21 | 9 | 34%
Task 5 | Person 5 | 2016-02-17 | 4 | 25%
Task 6 | Person 1 | 2016-02-20 | 6 | 7%
Task 7 | Person 2 | 2016-02-20 | 7 | 42%
Task 8 | Person 3 | 2016-02-22 | 5 | 34%
Task 9 | Person 4 | 2016-02-22 | 9 | 14%
Task 10 | Person 5 | 2016-02-23 | 6 | 55%
Task 11 | Person 1 | 2016-02-16 | 7 | 59%
Task 12 | Person 2 | 2016-02-17 | 9 | 41%
Task 13 | Person 3 | 2016-02-18 | 8 | 0%
Task 14 | Person 4 | 2016-02-20 | 7 | 49%
Task 15 | Person 5 | 2016-02-21 | 4 | 36%
Task 16 | Person 1 | 2016-02-21 | 6 | 54%
Task 17 | Person 2 | 2016-02-24 | 6 | 57%
Task 18 | Person 3 | 2016-02-25 | 4 | 22%
Task 19 | Person 4 | 2016-02-27 | 7 | 46%
Task 20 | Person 5 | 2016-02-16 | 3 | 100%
Task 21 | Person 1 | 2016-02-19 | 10 | 47%
Task 22 | Person 2 | 2016-02-21 | 5 | 55%
Task 23 | Person 3 | 2016-02-23 | 7 | 38%
Task 24 | Person 4 | 2016-02-26 | 7 | 33%
Task 25 | Person 5 | 2016-02-28 | 3 | 68%
Task 26 | Person 1 | 2016-03-01 | 9 | 88%
Task 27 | Person 2 | 2016-03-02 | 10 | 20%
Task 28 | Person 3 | 2016-02-16 | 4 | 10%
Task 29 | Person 4 | 2016-02-19 | 8 | 60%
Task 30 | Person 5 | 2016-02-22 | 10 | 34%
Task 31 | Person 1 | 2016-02-25 | 6 | 51%
Task 32 | Person 2 | 2016-02-25 | 4 | 48%
Task 33 | Person 3 | 2016-02-28 | 8 | 32%
Task 34 | Person 4 | 2016-03-01 | 9 | 42%
Task 35 | Person 5 | 2016-02-16 | 5 | 59%
Task 36 | Person 1 | 2016-02-19 | 3 | 31%
Task 37 | Person 2 | 2016-02-21 | 7 | 49%
Task 38 | Person 3 | 2016-02-22 | 10 | 16%
Task 39 | Person 4 | 2016-02-22 | 10 | 31%
Task 40 | Person 5 | 2016-02-22 | 3 | 11%

## Advanced Project Plan Template
Ultimate Project Plan Advanced Excel Template
The Most Powerful Project Planning Template on the Market
View Details 4
Our Most Popular Project Management Templates
Excel Templates | PowerPoint Templates | MS Word Templates
Browse All Templates4