## Details
Project Management Dashboard Excel Template
Works on Excel 2007 and Above
Info | Project Management Dashboard Excel Free Template helps to manage projects using Microsoft Excel. Free Project Plan and Gantt Chart Templates helps you to plan a project time-lines and resource. You can change the default data and formula to meet your needs. |  | Please Note: We have protected the worksheets to avoid the mistakes by chance. You can use the password 'PNRao' to unprotect the Worksheets
Usage | You can manage multiple projects using this Simple Project Management Excel Dashboard Template. We plan our resource and time-lines based on the requirements, deliverables and available team and bandwidth. Project Management Dashboard template helps you to track all the projects, tasks and its progress and status of each task and project. You can daily add the data to update the Dashboard. And share with your teams and customer/stakeholders to update the project status and progress in the Project meetings. This is the must have tool for every project Manager.
Please Share | Project Tracking/ Project Plan / Gant. Chart Template is a Free and lite version of ANALYSISTABS' Project Management Templates. Please feel free to use, modify and share with your coleagues. | Please check our Premium Templates Bundle, all you need for effective project planning, management and presentations. Our premium templates are professional, powerfull, easy to customize and unique in style. Please visit analysistabs.com and grab our powerfull templates for nominal cost.
Please Let us know your feedback |  |  |  | info@analysistabs.com
Templates By ANALYSISTABS.For more templates and tools, please visit us: |  |  |  | htps://analysistabs.com
Premium Templates
Visit Our BLOG
ANALYSISTABS.COM
Project Gantt. 4
Data Sheet4
Advanced Templates4

## Dashboard
Project Management Dashboard
Project 2 |  | 61 Days | Starts On: 13-Feb-16 |  |  | Ends On: 07-Mar-16 |  |  | 10 Tasks
49.2% | OVERALL PROGRESS | OBJECTIVE | MILESTONES |  |  | RESOURCE |  |  | DUE THIS WEEK
50.8% |  | Enter the Main Objective of the Project Here. You can have breif description about the Project, and Its Important Items. Enter the Main Objective of the Project Here. You can have breif description about the Project, and Its Important Items. | Milestone | Start Date | Due Date | Name | Role | Hours | Task /Activity | Due Date
|  |  | Milestone 1 | 2017-06-19 | 2017-06-29 | Person 1 | Developer | 35 | Task Name 1 to be Completed | 2017-06-19
|  |  | Milestone 2 | 2017-06-20 | 2017-06-30 | Person 2 | Coder | 70 | Task Name 2 to be Completed | 2017-06-20
|  |  | Milestone 3 | 2017-06-21 | 2017-07-01 | Person 3 | Tester | 80 | Task Name 3 to be Completed | 2017-06-20
|  |  | Milestone 4 | 2017-06-22 | 2017-07-02 | Person 4 | Developer | 35 | Task Name 4 to be Completed | 2017-06-21
|  |  | Milestone 5 | 2017-06-23 | 2017-07-03 | Person 5 | Coder | 70
|  |  | Milestone 6 | 2017-06-24 | 2017-07-04 | Person 6 | Tester | 80
|  |  | Milestone 7 | 2017-06-25 | 2017-07-05
|  |  | Milestone 8 | 2017-06-26 | 2017-07-06
TOP 3 RISKS/ISSUES
4 Risk or Issue 1 and Its Description. And the Solution Identified.
4 Risk or Issue 1 and Its Description. And the Solution Identified.
4 Risk or Issue 1 and Its Description. And the Solution Identified.
KEY NOTES
You can capture the important notes to be followed while executing this projects. It may be Business Rules. Or Quality Checking Points to be performed before delivering the Project. Or the Key deliverables which you have promissed to your client. Lorem ipsum dolor sit amet, consectetuer adipiscing elit. Maecenas porttitor congue massa. Fusce posuere, magna sed pulvinar ultricies, purus lectus malesuada libero, sit amet commodo magna eros quis urna. Nunc viverra imperdiet enim. Fusce est. Vivamus a tellus. Pellentesque habitant morbi tristique senectus et netus et malesuada fames ac turpis egestas. Proin pharetra nonummy pede. Mauris et orci. Aenean nec lorem. In porttitor. Donec laoreet nonummy augue. Suspendisse dui purus, scelerisque at, vulputate vitae, pretium mattis, nunc. Mauris eget neque at sem venenatis eleifend. Ut nonummy.
49%
Project Gantt. 4
Data Sheet4

## Project Plan
Please Select a Project to View Related Tasks & Gantt. |  |  |  | 4 |  | All Projects | 40 Tasks Found
| Project Plan |  |  | Tasks Scrool | Task ID | TaskS | Reponsible | Start Date | End Date | Days Req. | Status | Days Comp. | Project | 2016-02-12 | 2016-02-13 | 2016-02-14 | 2016-02-15 | 2016-02-16 | 2016-02-17 | 2016-02-18 | 2016-02-19 | 2016-02-20 | 2016-02-21 | 2016-02-22 | 2016-02-23 | 2016-02-24 | 2016-02-25 | 2016-02-26 | 2016-02-27
|  |  |  | 0 | 0 | 0 | 1 | 2 | 4 | 3 | 4 |  | -1
Project Name |  |  |  |  | 1 | Task 1 | Person 1 | 2016-02-16 | 2016-02-20 | 5 | 47% | 2.35 | Project 1
Customer Name |  |  |  |  | 2 | Task 2 | Person 2 | 2016-02-17 | 2016-02-22 | 6 | 43% | 2.58 | Project 1
Project Manager |  |  |  |  | 3 | Task 3 | Person 3 | 2016-02-18 | 2016-02-27 | 10 | 38% | 3.8 | Project 1
[5 empty] | 4 | Task 4 | Person 4 | 2016-02-21 | 2016-02-29 | 9 | 34% | 3.06 | Project 1
Start Date |  | 2016-02-12 |  |  | 5 | Task 5 | Person 5 | 2016-02-17 | 2016-02-20 | 4 | 25% | 1 | Project 1
End Date |  | 2016-03-12 |  |  | 6 | Task 6 | Person 1 | 2016-02-20 | 2016-02-25 | 6 | 7% | 0.42 | Project 1
Overall Progress |  | 41.95% |  |  | 7 | Task 7 | Person 2 | 2016-02-20 | 2016-02-26 | 7 | 42% | 2.94 | Project 1
|  | 58.05% |  |  | 8 | Task 8 | Person 3 | 2016-02-22 | 2016-02-26 | 5 | 34% | 1.7 | Project 1
Days Required 6 |  |  |  |  | 9 | Task 9 | Person 4 | 2016-02-22 | 2016-03-01 | 9 | 14% | 1.26 | Project 1
29 days |  |  |  |  | 10 | Task 10 | Person 5 | 2016-02-23 | 2016-02-28 | 6 | 55% | 3.3 | Project 1
266 ManDays |  |  |  |  | 11 | Task 11 | Person 1 | 2016-02-13 | 2016-02-19 | 7 | 59% | 4.13 | Project 2
[5 empty] | 12 | Task 12 | Person 2 | 2016-02-17 | 2016-02-25 | 9 | 41% | 3.69 | Project 2
Gantt. Scroll |  |  | 0 |  | 13 | Task 13 | Person 3 | 2016-02-18 | 2016-02-25 | 8 | 0% | 0 | Project 2
[5 empty] | 14 | Task 14 | Person 4 | 2016-02-20 | 2016-02-26 | 7 | 49% | 3.43 | Project 2
Total Tasks | 40 | Remarks |  |  | 15 | Task 15 | Person 5 | 2016-02-21 | 2016-02-24 | 4 | 36% | 1.44 | Project 2
Not Started(0%) | 1 |  |  |  | 16 | Task 16 | Person 1 | 2016-02-21 | 2016-02-26 | 6 | 54% | 3.24 | Project 2
Inprogress(1-99%) | 38 |  |  |  | 17 | Task 17 | Person 2 | 2016-02-24 | 2016-02-29 | 6 | 85% | 5.1 | Project 2
1-25% | 8 |  |  |  | 18 | Task 18 | Person 3 | 2016-02-25 | 2016-02-28 | 4 | 22% | 0.88 | Project 2
26-50% | 20 |  |  |  | 19 | Task 19 | Person 4 | 2016-02-27 | 2016-03-04 | 7 | 46% | 3.22 | Project 2
51-75% | 7 |  |  |  | 20 | Task 20 | Person 5 | 2016-02-16 | 2016-02-18 | 3 | 100% | 3 | Project 2
76-99% | 3 |  |  |  | 21 | Task 21 | Person 1 | 2016-02-12 | 2016-02-21 | 10 | 47% | 4.7 | Project 3
Completed(100%) | 1 |  |  |  | 22 | Task 22 | Person 2 | 2016-02-21 | 2016-02-25 | 5 | 79% | 3.95 | Project 3
[5 empty] | 23 | Task 23 | Person 3 | 2016-02-23 | 2016-02-29 | 7 | 38% | 2.66 | Project 3
[5 empty] | 24 | Task 24 | Person 4 | 2016-02-26 | 2016-03-03 | 7 | 33% | 2.31 | Project 3
Project Gantt. Template By: |  | https://analysistabs.com | PNRao |  | 25 | Task 25 | Person 5 | 2016-02-28 | 2016-03-01 | 3 | 68% | 2.04 | Project 3
Please let us know your feedback ¦ Email: info@analysistabs.com
Task Grid
Gantt Chart
42%

## Projects Summary
Project Summary | [5 empty] | Project 2
Projects | Tasks | Start | End | Days | %Progress
All Projects | 40 | 2016-02-12 | 2016-03-12 | 266 | 41.95% | Not Started(0%) |  | 1
Project 1 | 10 | 2016-02-16 | 2016-03-04 | 67 | 33.9% | Inprogress(1-99%) | 1-25% | 1
Project 2 | 10 | 2016-02-13 | 2016-03-07 | 61 | 49.2% |  | 26-50% | 4
Project 3 | 5 | 2016-02-12 | 2016-03-09 | 32 | 53% |  | 51-75% | 2
Project 4 | 7 | 2016-02-16 | 2016-03-12 | 51 | 44.43% |  | 76-99% | 1
Project 5 | 8 | 2016-02-19 | 2016-03-11 | 55 | 33.88% | Completed(100%) |  | 1
Project 6 | 0 | 0 | 0 | 0 | #DIV/0!
Project 7 | 0 | 0 | 0 | 0 | #DIV/0!
Project 8 | 0 | 0 | 0 | 0 | #DIV/0!
Project 9 | 0 | 0 | 0 | 0 | #DIV/0!
Project 10 | 0 | 0 | 0 | 0 | #DIV/0!
Formulas:
Start = MIN(Table1[Start Date])
Start = MIN(IF(Table1[Project]=[Projects],Table1[Start Date]))
End = MAX(Table1[Start Date])+MAX(Table1[Days Req.])
End = MAX(IF(Table1[Project]=[Projects],Table1[Start Date]))+MAX(IF(Table1[Project]=[Projects],Table1[Days Req.]))

## Data Sheet
Project | Task | Reponsible | Start Date | Days Req. | Progress
Project 1 | Task 1 | Person 1 | 2016-02-16 | 5 | 47%
Project 1 | Task 2 | Person 2 | 2016-02-17 | 6 | 43%
Project 1 | Task 3 | Person 3 | 2016-02-18 | 10 | 38%
Project 1 | Task 4 | Person 4 | 2016-02-21 | 9 | 34%
Project 1 | Task 5 | Person 5 | 2016-02-17 | 4 | 25%
Project 1 | Task 6 | Person 1 | 2016-02-20 | 6 | 7%
Project 1 | Task 7 | Person 2 | 2016-02-20 | 7 | 42%
Project 1 | Task 8 | Person 3 | 2016-02-22 | 5 | 34%
Project 1 | Task 9 | Person 4 | 2016-02-22 | 9 | 14%
Project 1 | Task 10 | Person 5 | 2016-02-23 | 6 | 55%
Project 2 | Task 11 | Person 1 | 2016-02-13 | 7 | 59%
Project 2 | Task 12 | Person 2 | 2016-02-17 | 9 | 41%
Project 2 | Task 13 | Person 3 | 2016-02-18 | 8 | 0%
Project 2 | Task 14 | Person 4 | 2016-02-20 | 7 | 49%
Project 2 | Task 15 | Person 5 | 2016-02-21 | 4 | 36%
Project 2 | Task 16 | Person 1 | 2016-02-21 | 6 | 54%
Project 2 | Task 17 | Person 2 | 2016-02-24 | 6 | 85%
Project 2 | Task 18 | Person 3 | 2016-02-25 | 4 | 22%
Project 2 | Task 19 | Person 4 | 2016-02-27 | 7 | 46%
Project 2 | Task 20 | Person 5 | 2016-02-16 | 3 | 100%
Project 3 | Task 21 | Person 1 | 2016-02-12 | 10 | 47%
Project 3 | Task 22 | Person 2 | 2016-02-21 | 5 | 79%
Project 3 | Task 23 | Person 3 | 2016-02-23 | 7 | 38%
Project 3 | Task 24 | Person 4 | 2016-02-26 | 7 | 33%
Project 3 | Task 25 | Person 5 | 2016-02-28 | 3 | 68%
Project 4 | Task 26 | Person 1 | 2016-03-01 | 9 | 88%
Project 4 | Task 27 | Person 2 | 2016-03-02 | 10 | 20%
Project 4 | Task 28 | Person 3 | 2016-02-16 | 4 | 10%
Project 4 | Task 29 | Person 4 | 2016-02-19 | 8 | 60%
Project 4 | Task 30 | Person 5 | 2016-02-22 | 10 | 34%
Project 4 | Task 31 | Person 1 | 2016-02-25 | 6 | 51%
Project 4 | Task 32 | Person 2 | 2016-02-25 | 4 | 48%
Project 5 | Task 33 | Person 3 | 2016-02-28 | 8 | 32%
Project 5 | Task 34 | Person 4 | 2016-03-01 | 9 | 42%
Project 5 | Task 35 | Person 5 | 2016-02-20 | 5 | 59%
Project 5 | Task 36 | Person 1 | 2016-02-19 | 3 | 31%
Project 5 | Task 37 | Person 2 | 2016-02-21 | 7 | 49%
Project 5 | Task 38 | Person 3 | 2016-02-22 | 10 | 16%
Project 5 | Task 39 | Person 4 | 2016-02-22 | 10 | 31%
Project 5 | Task 40 | Person 5 | 2016-02-22 | 3 | 11%

## Advanced Project Plan Template
Ultimate Project Plan Advanced Excel Template
The Most Powerful Project Planning Template on the Market
View Details 4
Our Most Popular Project Management Templates
Excel Templates | PowerPoint Templates | MS Word Templates
Browse All Templates4