## Project Plan
| Data Analysis - Project Plan Template | Get our Premium Project Management Templates
Project Management | Excel Template by Analysistabs.com
Info | Project Plan Template for Planning and Managing a Data Analysis Project.
Usage | Enter the Project Details and the Project Timelines in the Required Columns of the Data Table. And the Gantt chart is created automatically based on your data.
Please Share | Analysistabs.com is created for making useful templates for Project Management and Planning. Please share our file with your colleagues and friends, it helps us to create better tools and motivates us to build more templates based on the user suggestions.
Visit us
Advanced Templates4
Analysistabs.com
4 Download Now
Goto Template Sheet

## Project Plan Template
Project Name | Data Analysis Project Plan | [7 empty] | Gantt Chart
TOTAL TASKS | 21 |  | Duration | 90 |  | Overall Progress
Completed | 4 |  | Project Start | 2020-02-29
In progress | 8 |  | Project End | 2020-05-28 |  | 54.76%
Not Started | 9
45.24%
Phase/Tasks | Responsible | Start Date | End Date | Progress | Status | Duration | Completed | Pending
Understand & Plan | Person 1 | 2020-02-29 | 2020-04-10 | 100% | Completed | 42 | 42 | 0
Task Title 1 | Person 2 | 2020-02-29 | 2020-04-10 | 100% | In progress | 42 | 42 | 0
Task Title 2 | Person 3 | 2020-03-03 | 2020-03-07 | 100% | Completed | 5 | 5 | 0
Task Title 3 | Person 4 | 2020-03-02 | 2020-03-08 | 100% | In progress | 7 | 7 | 0
Data Processing | Person 5 | 2020-03-08 | 2020-04-10 | 93% | In progress | 34 | 32 | 2
Task Title 4 | Person 6 | 2020-03-08 | 2020-03-28 | 100% | Not Started | 21 | 21 | 0
Task Title 5 | Person 7 | 2020-03-18 | 2020-03-27 | 100% | In progress | 10 | 10 | 0
Task Title 6 | Person 8 | 2020-03-28 | 2020-04-10 | 80% | Not Started | 14 | 11 | 3
Data Analysis & Modelling | Person 9 | 2020-04-15 | 2020-05-28 | 45% | Not Started | 44 | 20 | 24
Analysis | Person 10 | 2020-04-16 | 2020-05-11 | 100% | Completed | 26 | 26 | 0
Modelling | Person 1 | 2020-04-15 | 2020-04-24 | 75% | In progress | 10 | 8 | 2
Validation | Person 2 | 2020-04-19 | 2020-05-10 | 0% | Completed | 22 | 0 | 22
Deployment | Person 3 | 2020-04-15 | 2020-05-28 | 0% | In progress | 44 | 0 | 44
Presentation | Person 4 | 2020-04-15 | 2020-05-11 | 25% | In progress | 27 | 7 | 20
Task Title 7 | Person 5 | 2020-04-15 | 2020-04-30 | 0% | Not Started | 16 | 0 | 16
Task Title 8 | Person 6 | 2020-04-20 | 2020-05-11 | 25% | In progress | 22 | 6 | 16
Task Title 9 | Person 7 | 2020-04-19 | 2020-04-30 | 0% | Not Started | 12 | 0 | 12
Documentation | Person 8 | 2020-04-16 | 2020-05-23 | 27% | Not Started | 38 | 10 | 28
Task Title 10 | Person 9 | 2020-04-16 | 2020-05-23 | 10% | Not Started | 38 | 4 | 34
Task Title 11 | Person 10 | 2020-04-21 | 2020-04-25 | 10% | Not Started | 5 | 1 | 4
Task Title 12 | Person 11 | 2020-04-21 | 2020-04-25 | 60% | Not Started | 5 | 3 | 2